## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE :-E-SUPERMARKET SYSTEM | [6 empty] | DEPARTMENT NAME | [6 empty] | Information Technology
PROJECT GUIDE :- Prof. Anagha Aher | [6 empty] | DATE | [6 empty] | 2022-01-30
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project Identifying the technology stack and functionalities of the Mini Project | Disha,Dhruvi,Pallavi | 2021-12-28 | 2021-12-31 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Discussing the project topic with the help of paper prototype. | Disha,Dhruvi,Pallavi | 2022-01-01 | 2022-01-09 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
WEEK 3 | Designing the graphical user interface and presentation I | Disha,Dhruvi,Pallavi | 2022-01-10 | 2022-01-16 | 1 | 100% | bar: WEEK 2 M to WEEK 3 W; WEEK 3 F
2 | Project Design and Implementation
WEEK 4 | Database design & Connectivity with front end | Disha,Dhruvi,Pallavi | 2021-11-11 | 2021-11-18 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 M to WEEK 5 F
WEEK 5 | Error, results and Report Writing & Presentation II | Disha,Dhruvi,Pallavi | 2021-11-19 | 2021-11-26 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F